## PIR Timeline
PIR Timeline - CHG1134187 (QA Vault DR Failover/Failback)
Date | Event
15 Jul 2025, 20:00:00 | CHG0976705 (QA DR exercise - 2025) executed.
02 Mar 2026, 11:00:00 | Functional test script updated - DR secondary ID expectation changed to dr-secondary-ausmponpremnp. This change was not reflected in the DR failover/failback scripts at the time.
28 Jul 2026, 20:20:00 | Scheduled QA DR failover exercise (CHG1134187) initiated using dr_drill_failover.sh.
28 Jul 2026, 20:30:00 | Asked network team to update the LB config to remove MW cluster from target group.
28 Jul 2026, 20:50:00 | Network Team did the LB config and confirmed.
28 Jul 2026, 20:52:00 | Script call to sys/replication/dr/secondary/update-primary timed out with 'context deadline exceeded'. Script's polling/retry loop did not resolve the underlying replication break.
28 Jul 2026, 21:20:00 | Replication between PRI and DR clusters confirmed broken.
28 Jul 2026, 21:30:00 | Incident raised to perform manual recovery.
28 Jul 2026, 21:35:00 | Manual remediation performed on primary server (qsmaa04l): vault write sys/replication/dr/primary/revoke-secondary, followed by regeneration of secondary token via vault write -f sys/replication/dr/primary/secondary-token. New token applied on secondary (auq5928s) via update-primary.
28 Jul 2026, 22:00:00 | Replication restored. BVT was started.
28 Jul 2026, 23:00:00 | BVT was successfully completed and Failback script (dr_drill_failback.sh) executed to restore original PRI/DR roles. Script completed, but functional tests reported a replication issue.
29 Jul 2026, 00:45:00 | Root cause identified: failback script set dr_secondary to dr-secondary-ausmponpremtmnp, while functional test script (per the 02 Mar change) expected dr-secondary-ausmponpremnp.
29 Jul 2026, 01:05:00 | DR secondary ID manually corrected to dr-secondary-ausmponpremnp to align with pre-change cluster config. Functional tests and BVT re-run and confirmed successful.
29 Jul 2026, 01:20:00 | Restoration BVT was completed successfully.
Note: Exact times for the 28 Jul entries should be filled in from the CHG1134187 change record / incident ticket for audit accuracy.